## Summary
Snags Points | Unit No. | Total
873
Painting | 41 | 41
Plumbing | 3 | 3
AC | 2 | 2
Elevator | 0 | 0
AV | 2 | 2
Electrical | 14 | 14
Carpentry | 12 | 12
Decking | 2 | 2
FAS | 3 | 3
False Ceiling | 0 | 0
Sliding Door & Windows | 14 | 14
Civil | 32 | 32

## Unit No 873
Unit 873 Pending Snags
SL NO | Location | Description | Status | Category | Snags to be closed by | Closure date | Remark
1 | Foyer Area | Lift Wooden frame not finished | Open | Carpentry | Projects
2 | Foyer Area | MCB Switch plate screw not fixed | Open | Electrical | Projects
3 | Foyer Area | Sprinkler cap not fixed | Open | FAS | Projects
4 | Foyer Area | Trap door not fixed | Open | Carpentry | Projects
5 | Foyer Area | VDC Not fixed | Open | AV | Projects
6 | Foyer Area | Door frame side wall crack | Open | Painting | Projects
7 | Foyer Area | Wall around Paint patch marks | Open | Painting | Projects
8 | Foyer Area | Floor marble chipped & Crack & Stain marks | Open | Civil | Projects
9 | Powder Room | Light not working | Open | Electrical | Projects
10 | Powder Room | Door frame side around gap | Open | Painting | Projects
11 | Powder Room | Light not working | Open | Electrical | Projects
12 | Powder Room | Floor marble chipped & wax filled, Scratches | Open | Civil | Projects
13 | Powder Room | Vanity Counter slab chipped & Scratches | Open | Civil | Projects
14 | Living Room | Sliding door lock frame not fixed | Open | Sliding Door & Window | Projects
15 | Living Room | Door Magic Eye not fixed | Open | Carpentry | Projects
16 | Living Room | Door frame side wall crack | Open | Painting | Projects
17 | Living Room | Fire Sprinkle cap aroud gap | Open | Painting | Projects
18 | Living Room | Fire sprinkler cap not properly fixed | Open | FAS | Projects
19 | Living Room | Wall Chipped | Open | Painting | Projects
20 | Living Room | Ceiling Crack | Open | Painting | Projects
21 | Living Room | Floor marble chipped & Crack & Stain marks | Open | Civil | Projects
22 | Living Balcony | Decking floor not fixed | Open | Decking | Projects
23 | Living Balcony | Sliding door lock not fixed | Open | Sliding Door & Window | Projects
24 | Living Balcony | Sliding door frame not fixed | Open | Sliding Door & Window | Projects
25 | Living Balcony | Dummy cap missing | Open | Sliding Door & Window | Projects
26 | Living Balcony | Sliding door glass scratches | Open | Sliding Door & Window | Projects
27 | Living Balcony | Wall Chipped | Open | Painting | Projects
28 | Living Balcony | Ceiling Crack | Open | Painting | Projects
29 | Living Balcony | Parapet glass chipped & scratches | Open | Sliding Door & Window | Projects
30 | Living Balcony | Decking floor not fixed | Open | Decking | Projects
31 | MBR | Light blinking | Open | Electrical | Projects
32 | MBR | Door frame side wall crack | Open | Painting | Projects
33 | MBR | Ceiling Crack | Open | Painting | Projects
34 | MBR | Ceiling paint patch marks | Open | Painting | Projects
35 | MBR | Window glass scratches & Dummy cap missing | Open | Sliding Door & Window | Projects
36 | MBR | Wooden floor gap | Open | Carpentry | Projects
37 | MBR | Wooden floor chipped | Open | Carpentry | Projects
38 | MBR | Wooden floor stain marks | Open | Carpentry | Projects
39 | MBR Bathroom | Door frame side wall crack | Open | Painting | Projects
40 | MBR Bathroom | Wall Chipped | Open | Painting | Projects
41 | MBR Bathroom | Ceiling Crack | Open | Painting | Projects
42 | MBR Bathroom | Wall Paint patch marks | Open | Painting | Projects
43 | MBR Bathroom | Bath tub trap door not present | Open | Civil | Projects
44 | MBR Bathroom | Wall tile chipped & scratches | Open | Civil | Projects
45 | MBR Bathroom | Wall tiles alignment not properly done | Open | Civil | Projects
46 | MBR Bathroom | Floor marble chipped & Scratches | Open | Civil | Projects
47 | Dining Hall | VDM Not fixed | Open | AV | Projects
48 | Dining Hall | Sprinkler cap near ceiling damaged | Open | Painting | Projects
49 | Dining Hall | Wall & Ceiling chipped & Stain marks | Open | Painting | Projects
50 | Dining Hall | Ceiling Crack | Open | Painting | Projects
51 | Dining Hall | Wall crack near AC Grill | Open | Painting | Projects
52 | Dining Hall | Floor marble chipped & wax filled, Scratches, around skirting not properly finished | Open | Civil | Projects
53 | Corridor | Ceiling Crack | Open | Painting | Projects
54 | Corridor | Wall Chipped | Open | Painting | Projects
55 | Corridor | Wall paint patch marks & stain marks | Open | Painting | Projects
56 | Corridor | Floor marble deep chipped & waxing done | Open | Civil | Projects
57 | Corridor | Skirting around not properly finished | Open | Civil | Projects
58 | Bedroom 1 | Wall paint patch marks & stain marks | Open | Painting | Projects
59 | Bedroom 1 | Wall Chipped | Open | Painting | Projects
60 | Bedroom 1 | Window frame & glass scratches, Dummy cap missing | Open | Sliding Door & Window | Projects
61 | Bedroom 1 | Wall corners chipped | Open | Painting | Projects
62 | Bathroom 1 | Light switch interchanged | Open | Electrical | Projects
63 | Bathroom 1 | Ceiling around gap | Open | Painting | Projects
64 | Bathroom 1 | Trap door around crack | Open | Painting | Projects
65 | Bathroom 1 | Vanity counter slab stain marks, Scratches, Wall & slab gap | Open | Civil | Projects
66 | Bathroom 1 | Wall tile chipped & gap | Open | Civil | Projects
67 | Bathroom 1 | Shower wall tiles chipped | Open | Civil | Projects
68 | Bathroom 1 | Wall tiles alignment not properly done | Open | Civil | Projects
69 | Bathroom 1 | Floor tiles scratches | Open | Civil | Projects
70 | Bathroom 1 | Floor tile alignment not properly done | Open | Civil | Projects
71 | Bathroom 1 | Floor tiles re-grouting required | Open | Civil | Projects
72 | Bedroom 2 | Around light fixture gap | Open | Painting | Projects
73 | Bedroom 2 | Window frame & glass scratches, Dummy cap missing | Open | Sliding Door & Window | Projects
74 | Bedroom 2 | Door frame side wall crack | Open | Painting | Projects
75 | Bedroom 2 | Wall chipped | Open | Painting | Projects
76 | Bedroom 2 | Ceiling paint patch marks | Open | Painting | Projects
77 | Bedroom 2 | Wooden floor near window gap | Open | Carpentry | Projects
78 | Bedroom 2 | Cupboard one drawer not properly opening | Open | Carpentry | Projects
79 | Bedroom 2 | Cupboard light not working | Open | Electrical | Projects
80 | Bedroom 2 | Wall corners chipped | Open | Painting | Projects
81 | Bathroom 2 | Window glass scratches | Open | Sliding Door & Window | Projects
82 | Bathroom 2 | Window door handle not working | Open | Sliding Door & Window | Projects
83 | Bathroom 2 | Window frame side wall gap | Open | Sliding Door & Window | Projects
84 | Bathroom 2 | Door frame side wall chipped | Open | Painting | Projects
85 | Bathroom 2 | Wall tiles stain marks | Open | Civil | Projects
86 | Bathroom 2 | Floor tiles stain marks | Open | Civil | Projects
87 | Bathroom 2 | Floor tiles around wall corner not finished properly | Open | Civil | Projects
88 | Bathroom 2 | Vanity Counter slab Scratches | Open | Civil | Projects
89 | Kitchen | Kitchen cabinet frame came out | Open | Carpentry | Projects
90 | Kitchen | Kitchen cabinet 3 model switch board not fixed | Open | Electrical | Projects
91 | Kitchen | Ceiling watermarks & paint patch marks | Open | Painting | Projects
92 | Kitchen | Window glass scratches | Open | Sliding Door & Window | Projects
93 | Kitchen | Floor tiles chipped | Open | Civil | Projects
94 | Kitchen | Wall crack & Chipped | Open | Painting | Projects
95 | Kitchen | Wall paint patch marks | Open | Painting | Projects
96 | Utility | Switches not fixed | Open | Electrical | Projects
97 | Utility | Door frame side wall crack & Chipped | Open | Painting | Projects
98 | Utility | Wall stain marks | Open | Painting | Projects
99 | Utility | Ceiling Crack | Open | Painting | Projects
100 | Utility | Floor tiles chipped | Open | Civil | Projects
101 | Utility | AC ODU area floor tiles chipped | Open | Civil | Projects
102 | Utility | AC ODU fins damaged | Open | AC | Projects
103 | Utility | Main DB SLD Not fixed | Open | Electrical | Projects
104 | Utility | DB SLD Not fixed & Dummy cap not fixed | Open | Electrical | Projects
105 | Utility | ELCB not working | Open | Electrical | Projects
106 | Utility | Floor one tile color mismatching | Open | Civil | Projects
107 | Maids Room | Wall deep chipped | Open | Painting | Projects
108 | Maids Room | Sprinkler cap not fixed | Open | FAS | Projects
109 | Maids Bath | EWC Not fixed | Open | Plumbing | Projects
110 | Maids Bath | Flushing plate not fixed (Tiles needs to be cut) | Open | Plumbing | Projects
111 | Maids Bath | Door not working properly | Open | Carpentry | Projects
112 | Maids Bath | Door frame dummy caps missing | Open | Carpentry | Projects
113 | Maids Bath | Light not working | Open | Electrical | Projects
114 | Maids Bath | Door frame side wall tiles not fixed | Open | Civil | Projects
115 | Maids Bath | Door frame side around gap | Open | Civil | Projects
116 | Maids Bath | Floor stain marks | Open | Civil | Projects
117 | Maids Bath | Floor tiles chipped | Open | Civil | Projects
118 | Maids Bath | Floor tiles color mismatch | Open | Civil | Projects
119 | Maids Bath | Wall tiles stain marks | Open | Civil | Projects
Common Points |  | Switch plates not fixed in all area | Open | Electrical | Projects
|  | All AC Not working | Open | AC | Projects
|  | Fan regulator knob not fixed in all area | Open | Electrical | Projects
|  | Trap door not fixed in all area | Open | Carpentry | Projects
|  | Shower cubical glass not fixed in all bathrooms | Open | Sliding Door & Window | Projects
|  | CP Fittings not fixed all Bathrooms | Open | Plumbing | Projects
|  | Door stopper not fixed in all doors | Open | Carpentry | Projects
|  | Snags | Points
|  | Painting | 41
|  | Plumbing | 3
|  | AC | 2
|  | Elevator | 0
|  | AV | 2
|  | Electrical | 14
|  | Carpentry | 12
|  | Decking | 2
|  | FAS | 3
|  | False Ceiling | 0
|  | Sliding Door & Windows | 14
|  | Civil | 32